## Issue
SL | Raised by | Date raised | Assigned to | Date resolved | Status | Source doc | Section | Issue | Resolution | Discussion
1 | Supriya (Dev) | 2018-02-28 | Ajai |  |  | SRS | Account Dashbord | seprate tab for Quick Order in Design
2 | Supriya (Dev) | 2018-02-28 | Ajai |  |  | SRS | Ship-To | Conflict between sprint 3 and sprint 2 for shipTo selection, where in sprint2 they have customization to allow change shipTo but in sprint 3 they have asked shipping address should not be edited for commercial customers PFA on SS01
3 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | HOMEPAGE-_V2 - Popular videos | Streaming Videos to be given.
4 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | HOMEPAGE-_V2 - Popular videos | View All Link in Popular Videos should be displayed in a seperate page?
5 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | HomePAGE-_V2 | Information regarding the "Training Calendar".
6 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | HomePAGE-_V2 - Footer part | Learn More inside "Featured Manufacturers" leads to what?
7 | Supriya (Dev) | 2018-02-22 | Prasanna |  | Design updated pending | Design | HomePAGE-_V2 - Footer part | Icons inside the Footer Part is Clickable or not? |  | 23-Feb Chetan: We are provinding Quick Order and Cart file upload in Single tab. Design needs to be updated
8 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | HomePAGE-_V2 - Footer part | Fb and Linkedin icons to be standardized.
9 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | HomePAGE-_V2 - Featured products | Featured Products->"Call for Buy" should be changed to "Call for Price".[Remove the button and add the text].
10 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | CATEGORY_PAGE | Design for "Welcome" after Login.
11 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | CATEGORY_PAGE | Before Login:Login and Register options should be there under "My account"[leftmenu].
12 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | CATEGORY_PAGE | After Login: All the other options should be displayed.
13 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | CATEGORY_PAGE | Instead of "Cart File Upload" option under "My account"[leftmenu], text should be changed to "Quick order Pad"
14 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | Grid page v2 | click for quantity break
15 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | Part number | List page->"Multiselection" option is there. Grid Page->"Multiselection" option isn't there.
16 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | Detail Page | More options" to be changed to " Similar Products"
17 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | Locations Page | MAP
18 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | Vendor detail page | Functionality Part
19 | Supriya (Dev) | 2018-02-28 | Prasanna |  |  | Design | Checkout | Have an eye->Same functionality?
20 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Homepage | 1) TRAINING == Events page? and is this Static page? 2) as per standart we give default text read with in search field, Do we get default text? 4) Call to Buy button for featured products , is it indication of Price is 0 or do show call of price for all featured products? 5) 'In the news' is it related to blog or static text? what is the landing page clicking on 'Read more news' ? 6) Footer - on click on Online self services, Mfg Index- lands on which page? link needed. 7) We should show standard branding image for Facebook and Linked In 8) Copyright year- Need to update(2018) 9) need design for customization of having Support Team Details in header *inside sales person name, email, phone *outside sales person name, email, phone 10) Is this banner or clickable images(if yes, lands on which page?) links needed 11) lands on which page? static page links and designs needed General comment: design and links needed for all static and landing pages from homepage
21 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item List/Grid Functionality | In List page- there is 'Select Item' check box In Grid page - there is no 'Select Item' check box --> Which should be followed? Do we need to have in both or only for list page
22 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item List/Grid Functionality | Click for Quantity Break --> What is the entry point for Quantity Break? List page or detail?
23 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item List/Grid Functionality | In List page- Best seller with no dropdown In Grid page - Best seller with dropdown --> Which should be followed? Do we need to have in both or only for grid page
24 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item/Product Detail Functionality | Product groups (SRS) vs my favourites (Design) -> which one should be followed?
25 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item/Product Detail Functionality | how to handle superceeded/obsolete item in quick entry pad , do we get an alert message?
26 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item/Product Detail Functionality | Link to Share product vs Send link -> Which one should be followed?
27 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item/Product Detail Functionality | More Options -> Is this same as Similar products?
28 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Item/Product Detail Functionality | Do we have Send and print link in detail [page for superceeded/obsolete item?
29 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Registration | Registration template is missing for all the users
30 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | User Login | Design template is missing
31 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Shopping Cart | Clear card vs empty cart -> which one should be followed?
32 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Shopping Cart | No Review order check box vs Review order check box -> which one should be followed?
33 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Checkout by PO - order details | (1) Order notes, (2) required by and (3) order vias fields are not present in design
34 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Checkout by PO - order details | SRS - “Checkout by PO” AND “Checkout by Credit Card” are present Design - Purchase Order and Credit Card are present --> which one should be followed?
35 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Order confirmation | SRS - Print and Send Buttons Design - Print link is present and no send button --> which one should be followed?
36 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Order confirmation | Display the following: CONTACT INFORMATION: Contact Name / Email ID ORDER CONFIRMATION : SXe OE #, PO Number, Order Value, Carrier code LINE INFORMATION: Item Number, Customer Item Number ( as a note under description ), Extented Cost --> This is not present in the design
37 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Order confirmation | SRS - Cost is present Design - Price is present --> Which one should be followed?
38 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Contact information | No Last Login details preesnt in SRS but absent in design -> which one should be followed?
39 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Contact information | Design template is missing
40 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Open Order & Order History | Design template is missing
41 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | User Roles (APA Module) | Design template is missing
42 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Save Cart | Email button missing in the design for logged in users to send/email the cart
43 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Save Cart | Discrepancies found in the list of fields to be displayed in save cart page. Design is not in sync with SRS
44 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Product groups | Discrepancies found in the list of fields to be displayed in product group page. Design is not in sync with SRS
45 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Chat | Design template is missing
46 | Prabhu (QC) | 2018-02-28 | Prasanna |  |  | Design | Social Media | Discrepancies found in the list of social media icons to be displayed